## Sheet1
Project name | Accent Recognition
Project Guide name
Mentor name(IBM) | Mr. Sumit Shukla
Team members | Aditi Kulkarni, Dhaval Solanki, Ishaan Thanekar & Mayank Subramanian
Description | The goal of this project is to use machine learning to dissect and leverage the rich information contained in company earnings transcripts – i.e. the written transcripts of the quarterly earnings calls held by the management of publicly held companies – to predict whether the companies’ stock prices will rise or fall. Students should use machine learning algorithms such as Naïve Bayes algorithm to eliminate noise, stop words and punctuation, and splitting it into individual sentences. The classification methodologies should be engaged to classify earning transcript into 3 separate buckets to be able to run more fine-grained analysis: i) main body of the earnings transcripts (usually pre-scripted), ii) questions asked by the large banks’ financial analysts, and iii) answers by management to these questions.
Slno | Task | Assigned to | Start date | End date | Status | Remarks
Week 1
1 | Understand the project given to you and discuss within team mates on how to step wise progress with it. Basically we need a project flow document or synopsis on the topic given to you | All team mates |  |  | Assigned
2
3
Week 2
1 | Frontend Setup | M.S.L.V. Saranya
2 | Dataset collection and pre-processing | Sonali Nanda
3
Week 3
1 | Loading csv dataset to mysql locally | Aditya Narayan Panda
2 | Individual Dashboard Prototype as ipynb | Bhandari Sree Shivani
3 | Designing on Figma | Bhandari Sree Shivani
Week 4
1 | Backend Setup using Django and creating model as sqlite database | Aditya Narayan Panda
2 | Frontend Homepage Designing | Sonali Nanda
3 | Frontend Individual Dashboard entry point Designing | M.S.L.V. Saranya
Week 5
1 | API created on Django Rest Framework | Aditya Narayan Panda
2 | Frontend Grouped Dashboard entry point Designing | Bhandari Sree Shivani
3
Week 6
1 | Connecting backend to frontend | Sonali Nanda
2 | Analysis of retrieved data to gain information in the frontend | M.S.L.V. Saranya
3 | Creating the final Dashboard based of the information in the frontend | Aditya Narayan Panda